Monad Dev Pipelining integration with DevWeb3Jogja’s existing program.

Study Group is a program of DevWeb3Jogja which has been running consistently for 3 years. As per our discussion points, the Study Group will be modified to address Monad Dev Pipelining targets. Where every founder gets connected to Monad directly, for consultation and Those targets are:

- Onboard new developers

- Contribute Monad DevTools

- Register to DeltaV

- Project regulatory

Two tracks, three sessions each.

## Before Blitz

- Preparation day:

  - Onboard new developers into  the study group

  - Walk them through the Monad ecosystem and MonSkills

  - Deploy first testnet so nobody turns up to the Blitz cold.

- Ideation:

  - Find ideas that actually fit Monad

  - Real research time, looking for new protocols

  - Build on top of the ecosystem instead of rebuilding what's already there

- Advanced session:

  - Take the ideas and build a working app

  - Live demo. Teams should walk into the Blitz with something already running.

## After Blitz

- Post-Blitz review:

  - Go through what each team built.

  - Find the gap and push winners further

  - Find what's fixable and fix it for non-winners

- Compounding cycle:

- Work through the feedback each team got in the review

- Check how far the project has actually moved since then

- Ask what impact it's having so far

- Builder meet-up:

  - Swap the tools teams actually used

  - Give Delta V a proper intro through what's coming next from Monad

## Timeline (rough)

Before Blitz:

- Preparation Day: 4 weeks before Monad Blitz

- Ideation: 3 weeks before Monad Blitz

- Advanced sessions: 2 weeks before Monad Blitz (runs weekly)

After Blitz:

- Post-Blitz review: 1 week after Monad Blitz

- Compounding cycle: 3 weeks after Monad Blitz (runs bi-weekly for 2 weeks)

- Builder meet-up: 2 months after Monad Blitz

Monad Blitz Jogja lands on the 3rd or 4th week of September. Have 3 (three) locations currently in discussions. 2 (two) being hotels, 1 (one) being indoor basketball arena.

Budget estimate (first pass)

The main event venue, contract, and first payment sit on our side separately.

- Session venue and space (Before + After): $50/session

- F&B across the sessions: $40/session

- Mentor and speaker for the advanced and demo sessions: $150/session

additionals:

- Ops and materials: $200/Monthly. (Claude subscriptions) *for Participants, 1 subscription account divided by 15 participants. Form of subsidy

- Buffer: $100. (Each Before Blitz & After Blitz)